## Business Aim 1
Zest Action Plan
Business Aim 1 - Zest is recognised as a leading provider of online movement and arts resources to improve health & wellbeing across the UK residential and domiciliary care sector.
Objectitive 1a | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
To increase usage, expand reach, and retain subscriptions across care homes | Transition (at least) 2 Beta customers to new portal (with cost benefit or free props) & extend subs as Zest 'Ambassador' homes. | Wellmoor & RP | [6 empty] | Not started
| Evaluate Beta subsc & develop customer engagement & marketing plan including referrals and incentives (branded prop & free activity content) https://docs.google.com/document/d/10GM5rtuBBBpKkwTrPTF1HK8IVhu97XVK/edit?usp=sharing&ouid=112749078273165764688&rtpof=true&sd=true | Wellmoor & RP | [6 empty] | Not started
| Maintain usage in Ambassador homes with monthly customer support & monitoring | Wellmoor (KT) & RP | [6 empty] | Not started
| Increase paid subs to 18 through networking and word-of-mouth referral (mix of new and retained customers) | Wellmoor |  |  |  |  | Sept 24-Mar 25 | Richard will review and reply | Not started
| Increase paid subs to 100 (mix of new and retained customers) | Wellmoor |  |  |  |  | Apr 25-Mar 26 |  | Not started
| Increase paid subs to 300 paying £500/year = £150k subs income (mix of new and retained customers) | Wellmoor |  |  |  |  | Apr 26-Mar 28 | Assuming base of 300 subcribers year on year allowing for attrition and new uptake | Not started
Not started
Objectitive 1b | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
To build brand identity, raise awareness and increase Zest's profile in the care sector | Launch Zest v3 portal March 2024 (with updated comms and marketing plan agreed) | BSO | [5 empty] | Who writes and implements comms and marketing plan? budget spend in current financial year on print / promo material? | Not started
| Increase Zest engagement via Care Sector Roadshow (May 2024) and other sector networking events | Wellmoor & RP | [5 empty] | What other sector events, is this realistic? suggest Wellmoor may be attending health & social care events / networking and this could piggyback to make ths achievable? | Not started
| Social media channels and messaging campaign Apr - Oct 24 that is achievable given limited resourcing | BSO | [5 empty] | 1 social media post per fortnight / month | Not started
| Develop care sector advocacy plan - trade publication articles, networking, champions and ambassadors | Wellmoor | [6 empty] | Not started
| Create and produce branded physical assets for display in the care home inc Move More Challenge planners | RP/Wellmoor | [5 empty] | Raise awareness with staff and residents in participating care homes and encourage regular usage | Not started
Objectitive 1c | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
To maintain the high performance of Zest, renewing content and evaluating engagement and quality | Implement Zest improvements based on (quarterly) customer, critical friend and sector feedback review | Partnership (BSO, Wellmoor, CP, ViA) | [5 empty] | Clarify what this includes | Not started
| Develop V2 Welcome pack and maintain effective onboarding for new customers including developing digital befriending support | Wellmoor |  |  |  |  | Oct 24-Oc 25 |  | Not started
| Maintain Zest website - content and website updates | Studio Deville | [6 empty] | Not started
Objectitive 1d | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
Develop new Zest product features in response to opportunity, relevance & sector evolution | Develop & test hybrid music delivery model (PoM) | Villages in Action |  |  |  |  | 2027 | Funding dependent | Not started
| Product development and innovation action learning sets (meet every 2 months) to explore areas for future dev/innovation & grant-funded project work: *Develop and test 5-a-day style campaign *Year-long programme of use with digital champions (younger folk - pathways into care) *Domicillary care application | Partnership (BSO, Wellmoor, CP, ViA) | [5 empty] | Quarterly 'labs' - could be fairly light touch - briging team together to respond to opportunities and drive product development / innovation | Not started
| Explore potential for personalised playlist or recommender tools | Partnership (BSO, Wellmoor, CP, ViA) | [6 empty] | Not started
| Increase segmented content for specific resident groups (eg bed bound or LWD) and favourites/personalisation | CP | [5 empty] | Funding dependent | Not started
| Develop & test staff training modules (VocTech) | Wellmoor | [5 empty] | Funding dependent | Not started
KEY
Green = essential
Yellow = funding dependent
Red = nice to have

## Business Aim 2
Zest Action Plan
Business Aim 2 - Zest has established itself as resilient, sustainable and socially responsible and cares about our impact.
Objective 2a | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
Maintain a partnership of practice (and vehicle enabling Zest to grow with subscription growth) | Develop Partnership of Practice agreement | BSO | [5 empty] | Proposed 3 month extension on current agreement beyond Feb | Not started
| Agree action plan for short term holding of specific work strands & how / who is co-ordinating | Partnership (BSO lead with CP) plus Wellmoor, ViA | [5 empty] | Quarterly or bi-monthly / monthly gatherings of this group? Mar-Oct? | Not started
| Review options for development of a trading vehicle / separate entity | Partnership (BSO, Wellmoor, CP, ViA) | [6 empty] | Not started
Not started
Objective 2b | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
Increase the financial stability of a right-sized service which can grow and innovate | Fundraising strategy, process for partner consensus, and pipeline established and reviewed quarterly | Partnership (BSO, Wellmoor, CP, ViA) (who driving?) | [5 empty] | Current pipeline bids submitted / in development: POM £6k over 3 years ViA decision mid Feb; VocTech £60k 6 months (Jun-Dec) Wellmoor submitted stage 1 end Jan; Stage 2 Feb; TNL bid to shape / scope and subit ideally by end Mar | Not started
| Budget & staff resource planning to facilitate subscription growth | Partnership (BSO, Wellmoor, CP, ViA) (who driving?) | [5 empty] | Quarterly financial planning/ review key metrics | Not started
| Scope out potential Angel Investors | Partnership (BSO, Wellmoor, CP, ViA) (who driving?) | [6 empty] | Not started
| Pitch for social investment | Partnership (BSO, Wellmoor, CP, ViA) (who driving?) | [6 empty] | Not started
| Test diversification of income models (training, resources, props/merch) | Partnership (BSO, Wellmoor, CP, ViA) (CP driving) | [6 empty] | Not started
Not started
Objective 2c | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
Successfully measure, evidence, and report our impact annually | Implement impact monitoring and evaluation tools | Partnership (BSO, Wellmoor, CP, ViA) (who driving?) | [5 empty] | March 24: Distill learning from Impact scale up phase, set new intended outcomes (psycho-social &/or health), updated iteration Zest Theory of Change and monitoring & evaluation plan. Set monitoring & evaluation priorities: - usage/subcription - content - evaluating outcomes & impact for residents/care homes | Not started
| Produce annual impact report | CP | [5 empty] | Y1 Q1 will be impact report from Scale Up & provide a baseline for future reviews | Not started
Not started
KEY
Green = essential
Yellow = funding dependent
Red = nice to have

## Business Aim 3
Zest Action Plan
Business Aim 3 - Zest is a pillar of best practice that learns, collaborates, and advocates across the arts and care sectors.
Objectitive 3a | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
Increase Zest relevance and efficacy through co-design/collaboration with care homes, sector engagement, advocacy and learning | Explore embedding user group (staff & residents) within stakeholder / governance models | Partnership (BSO, Wellmoor, CP, ViA) | [5 empty] | eg as per Age Friendly Manchester culture champions - became a co-commissioning panel | Not started
| Work towards Skills for Care endorsement | Wellmoor | [6 empty] | Not started
| Arts Sector comms (eg. Arts Council roundup or other) | BSO comms (March tbc) | [6 empty] | Not started
Objectitive 3b | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
Increase care staff skills and confidence through the development of enhanced training and resource packages | VocTech or other funder: Develop + test updated programme of in-person and digital training/resource for care staff (Care Home & Away Day staff training) a) Move More challenge b) Carers ability to translate activity for different settings, based on learnings from hybrid in-person care home test Jan-Feb 24 | Partnership (BSO, Wellmoor, CP, ViA) | [5 empty] | Funding dependent NB this is also referred to in 1d in terms of Product Development but it does relate to staff skills too so can we have it in both places? | Not started
| Develop Move More Challenge resources as a 'way in' for staff to apply the content | CP/RP (with budget line) | [5 empty] | Needs a timeframe | Not started
| Research & develop plan 4 self-financing training sessions for 25 staff | CP/RP | [6 empty] | Not started
Not started
Objectitive 3c | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
To remain at the forefront of knowledge and practice (arts and health, arts and digital) | Continue to centralise/share arts & care knowledge from events/learning including Care Sector roadshow | Partnership (BSO, Wellmoor, CP, ViA) (MG leading) | [5 empty] | 6 monthly market research review and collation (where resources allow) removed. | Not started
| Develop the skills of and advocate for specialist artistic practice related to arts & health, and delivering targeted arts content using digital technology. Seek ways to grow this practice through working with artists across movement, music and other artforms. | Content group (BSO, ViA, CP, RP) | [5 empty] | South West arts sector focus with national outputs | Not started
Objectitive 3d | Task Description | Owner | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2-5 Completion Date | Notes | Progress Update
To explore avenues for research-based collaboration | Strengthen body of evidence through funded project work (PoM, VocTech); connect with specialist evaluator to review and advise on evolving evidence base | ViA/ Wellmoor | [6 empty] | Not started
| Develop links for potential research partnerships to design research and submit for funding | tbc. Dmitri? or Partnership | [6 empty] | Not started
| Deliver funded research testing and assessing ways to increase wellbeing and physical activity levels (using digital resources for scalability) | Specific Partnership | [5 empty] | Welcome centre Exeter, Uni Bristol | Not started
| Have an open invitation for artists working in socially engaged ways within care settings to approach us if they are looking for partners/ wanting to use Zest in their own development | Villages in Action/ Bournemouth Symphony Orchestra? | [6 empty] | Not started
KEY
Green = essential
Yellow = funding dependent
Red = nice to have